## Sheet1
Review Date | Ticket No | Customer | Create On | What is required ? | Owner | Current Status | ETA | New ETA | Action | Action Details | Ticket Owner Comments
2021-03-10 | SR2682551 | RMC | 2020-09-21 | Automated Report to be configured | Vignesh | Resolved | 2021-03-11 |  | Close | Follow up with customer, if they need it we need to configure, else we can close the ticket. | Resolved
2021-03-10 | IM2750933 | TAGIC | 2020-11-19 | Asset dump download | Mahesh | Work in Progress | 2021-03-11 | 2021-03-12 | Close | Mahesh to talk to anand figure out the solution and fix it. | 11th Mar: End Date Revised
2021-03-10 | SR2758938 | RMC | 2020-11-26 | Automated Report to be configured | Vignesh | Resolved | 2021-03-11 |  | Close | Follow up with customer, if they need it we need to configure, else we can close the ticket. | Resolved
2021-03-10 | IM2769779 | HMCL | 2020-12-04 | Created time is greater than resolved time. | Mohammed | Resolved | 2021-03-11 |  | Close | Issue is fixed in March release, need to check with customer for new tickets, rectify the old tickets with L2 team help and close this ticket. | Closed and confirmed
2021-03-10 | SR2776860 | HMCL | 2020-12-10 | Add workgroups to EU Monthly and EU Weekly report | Aravind | Resolved | 2021-03-11 |  | Close | Attach the customer's email where they said it is not required, mention that it is open for a long time now and ask to create a new ticket if this is needed in future and close the ticket. | Closed and confirmed
2021-03-10 | IM2806674 | KLI | 2021-01-05 | Previous User history (Assignment history) | Mohammed | On Hold (Customer) | 2021-03-15 | 2021-03-22 | Close | Feature released in March cycle, follow up with customer and close the ticket. | 16th Mar: DR to PROD Movement is not done, Hence extending the ETA
2021-03-10 | IM2807685 | KLI | 2021-01-06 | Duplicate Password Expiry Notification | Mahesh | On Hold (Customer) |  | 2021-03-12 |  | Need to fix the issue | 11th Mar: End Date Revised
2021-03-10 | IM2808363 | RMC | 2021-01-06 | Created time is greater than resolved time. | Venkat | Resolved | 2021-03-11 | 2021-03-19 | Close | Issue is fixed in March release, need to check with customer for new tickets, rectify the old tickets with L2 team help and close this ticket. | 11th Mar: Not verified Properly 12th Mar: Not verified Properly 16th Mar: Verification is Done, old ticket still has issue yet to be resolved. 18th Mar: Yet to be completed, Vignesh to help venkat in this. Required input has been provided.
2021-03-10 | IM2815894 | EFL | 2021-01-12 | Not getting any tickets for approval | Aravind | Resolved | 2021-03-11 | 2021-03-12 | Close | Aravind to coordinate with Rajaiah and close this ticket. | 11th Mar: Awaiting User Confirmation, End Date Revised
2021-03-10 | IM2821525 | TAGIC | 2021-01-16 | Escalation Matrix and to be configured and helpdesk number to be updated in all the notification emails | Venkat | Resolved | 2021-03-11 | 2021-03-16 | Close | Configuration to be complete and ticket to be closed. | 11th Mar: Yet to be closed 12th Mar: Connectivity Issue, did not close the ticket 16th Mar: Connectivity Issue, did not continue the configurations.
2021-03-10 | SR2835148 | RMC | 2021-01-27 | Dashboard changes for Ajay Angello (Replication of one dashboard for Pharma is pending) | Aravind | Work in Progress | 2021-03-16 |  | Close | Aravind to coordinate with Natarajan and close it. | 19th Mar: Need to add a CSHTML file to complete the dasbhboard activity. Aravind to talk to anand and come up with a date to close this. 24th Mar: Tested and working in Dev Environment, will be pushed to Production as part of April Release.
2021-03-10 | IM2835284 | EFL | 2021-01-27 | Nikita Asset Management Case | Vignesh | On Hold (Customer) | 2021-03-19 |  |  | Aravind/Natarajan/Vignesh to discuss tomorrow and comeup with the next steps. | 11th Mar: Send for approval, additional Confirmation Provided by natarajan for the Asset Fields 16th Mar: Approval is received, ETA Given 18th Mar: Work is in progress, it has been discussed with EFL team and confirmed. 19th Mar: Will be completed by Today EoD. 23rd Mar: Nikitha to signoff for Server entity, then it will be replicated for the rest of the entities 24th Mar: Replication is done, Vignesh to close the ticket stating that this is a project and we have already done the configurations in UAT, production replication will be done considering it as a project and ticket is not required.
2021-03-10 | IM2841327 | KLI | 2021-02-01 | Users are not getting OTP | Sweta | Resolved | 2021-03-11 | 2021-03-12 | Check and Update | Need to check with Mahesh on the current status of this. Sweta to speak to Mahesh and come up with the update. | 11th Mar: ETA Revised Post Confirmation from Mahesh 16th Mar: Mail sent to parikshit to allow the Mumbai URL. Waiting for his response.
2021-03-10 | SR2844980 | KLI | 2021-02-03 | New Report to get a list of ticket reassigned by Service Desk | Vignesh | On Hold (Customer) | 2021-03-11 | 2021-03-19 | Close | Finalize the sp, configure the report and close the ticket. | 12th Mar: Yet to finalize the SP, Configuration is yet to completed. 16th Mar: Mohammed is on leave, team doesn't have an update. Ticket yet to be closed. 18th Mar: L2 team to help in this to write the SP and close this. Ticket is reassigned to Vignesh. 19th Mar: Natarajan & Vignesh to discuss today and close. 23rd Mar: Natarajan & Vignesh to discuss today and close. 24th Mar: Report is created and verified by KLI Team, 1 additional field to be added in the report, Vignesh to add this get the confirmation and close the ticket.
2021-03-10 | SR2847548 | CIS | 2021-02-05 | Need to enable feature "Mandatory refer article while ticket creation" | Vignesh | Resolved |  |  |  | The KM Module related activities to be completed, post which we will enable this feature. | 11th Mar: Awaiting User Confirmation, End Date Revised 12th Mar: Closed as it is a Duplicate ticket.
2021-03-10 | SR2851271 | Automation | 2021-02-08 | Autoticket for cloudapp support | Aravind | Resolved | 2021-03-11 |  | Close | Take confirmation from Raghavendra Seshu Murthy and Close the ticket. | Closed, New ticket will be created as needed.
2021-03-10 | SR2851582 | RMC | 2021-02-08 | Bulk Update issue | Venkat | On Hold (3rd Party) | 2021-04-11 |  |  | Bug fix in progress by Dev team, will be fixed in April release.
2021-03-10 | SR2853259 | CIS | 2021-02-09 | Reporting Manager and BU HR in CC of approval email. | Vignesh | Resolved | 2021-04-11 |  | Close | Feature for RM in CC is release in March. Team to test this with configuration and replicate the configuration for Leave reversal approvals, and mention that BU HR is not feasible and close the ticket. | 11th Mar: Feature did not work as expected, it has to be reverfied with the help of Development team. 18th Mar: The code change required for 1st Level to accommodate manager in CC is also done. Vignesh/Aravind to test and close this.
2021-03-10 | SR2857896 | RMC | 2021-02-12 | Ticket SLA Location to be made Mandatory while resolving a ticket, and updating a ticket | Mohammed | On Hold (3rd Party) | 2021-04-11 |  |  | Dev team to work and fix this in April release.
2021-03-10 | SR2858211 | KGI | 2021-02-13 | Receiving Old Notification | Mohammed | Resolved | 2021-03-11 | 2021-03-12 | Close | Fix explained by Natarajan To be implemented and closed. | 16th Mar: Fix yet to be implemented and no status as Mohammed is on leave. 18th Mar: Customer wants to observe for few more days. Mohammed to talk to customer and ask for observation end date, and close the ticket post that date if there is no response.
2021-03-11 | SR2867998 | CIS | 2021-02-19 | Duplicate ticket (Ref: SR2847548) | Vignesh | On Hold (Customer) | 2021-03-11 |  | Close | Duplicate ticket, already reference ticket is available, we will operate on only one ticket. | 11th Mar: Awaiting User Confirmation, End Date Revised 12th Mar: Customer Provided Confirmation, we need to enable feature. 16th Mar: Natarajan to provide Input. 18th Mar: CIS to discuss with HR and Other stakeholders and come back with confirmation to enable the force refer article feature on EUP. 19th Mar: CIS IS yet to get back to us. 23rd Mar: CIS Is yet to get back to us. Vignesh to follow up once. 24th Mar: CIS is yet to get back to us.
2021-03-11 | SR2868846 | KLI | 2021-02-19 | Additional Column to be added in Dashboard "Unassigned" drilldown. | Mohammed | Resolved | 2021-03-12 |  | Close | Natarajan To help | 12th Mar: Issue Identified, in SP the change is not replicated to all queries. 16th Mar: Mohammed is on leave, team doesn't have an update. Ticket yet to be closed.
2021-03-11 | IM2875114 | KLI | 2021-02-24 | Bulk Update issue | Sweta | On Hold (3rd Party) | 2021-04-11 |  |  | Bug fix in progress by Dev team, will be fixed in April release.
2021-03-11 | SR2875789 | CIS | 2021-02-24 | Additional field to be added in Resolved Notification | Vignesh | Resolved | 2021-03-12 |  | Close | To be closed. | 12th Mar: Will be closed today
2021-03-11 | IM2879193 | EFL | 2021-02-26 | No. of users used the ADSS Portal from Nov 2020 to till date. | Sweta | Resolved | 2021-03-12 | 2021-03-16 | Close | Dependency on RMC, Follow Up, Escalate, Get access, pull data and send to customer and close it. | 16th Mar: Today we have a call scheduled for the remote session at 8:00 PM, So ideally data should be provided, and ticket to be closed.
2021-03-11 | SR2880494 | KLI | 2021-02-27 | Add Location field all Email Templates | Vignesh | Resolved | 2021-03-12 | 2021-03-19 | Close | Configure and close. | 12th Mar: Only by Monday we can close this ticket. 16th Mar: Taking a lot of time than expected, hence moving the ticket to Vignesh. ETA also revised, from 15th to 16th. 18th Mar: Configurations done, customer wants to observe till EoD today, Vignesh to close the ticket on 19th.
2021-03-11 | IM2882619 | KLI | 2021-03-01 | ADSS In Password field "Eye" icon, is not showing the password on click. | Venkat | Resolved | 2021-03-12 |  | Close | Mahesh has fixed this, Venkat to follow up with Mahesh and get this deployed | 16th Mar: Taking a lot of time than expected, hence moving the ticket to Aravind. ETA also revised, from 15th to 16th.
2021-03-11 | SR2882771 | HMCL | 2021-03-01 | On call H/W, and On Call S/W in weekly and monthly report | Venkat | Resolved | 2021-03-12 |  | Close | Changes already deployed, Followup and Close. 8th March report it is already reflecting
2021-03-11 | IM2886019 | KLI | 2021-03-03 | OTP Issue | Venkat | Resolved | 2021-03-12 |  | Close | Mahesh will deploy on 12th Mar, Venkat to follow up and close | 16th Mar: Mail sent to parikshit to allow the Mumbai URL. Waiting for his response. 19th Mar: Awaiting user confirmation
2021-03-11 | SR2886362 | HMCL | 2021-03-03 | DSAT Was given, but DSAT Email is not received. | Mohammed | Resolved | 2021-03-12 |  | Close | Explain to the customer and take a confirmation and close the ticket. | 12th Mar: Awaiting Customer Confirmation. 16th Mar: Mohammed is on leave, team doesn't have an update. Ticket yet to be closed.
2021-03-11 | IM2887297 | KLI | 2021-03-04 | OTP Issue | Venkat | Resolved | 2021-03-12 |  | Close | Mahesh will deploy on 12th Mar, Venkat to follow up and close | 16th Mar: Mail sent to parikshit to allow the Mumbai URL. Waiting for his response.
2021-03-11 | IM2887519 | KLI | 2021-03-04 | OTP Issue | Venkat | Resolved | 2021-03-12 |  | Close | Mahesh will deploy on 12th Mar, Venkat to follow up and close | 16th Mar: Mail sent to parikshit to allow the Mumbai URL. Waiting for his response. 19th Mar: Awaiting user confirmation
2021-03-11 | IM2887984 | KLI | 2021-03-04 | OTP Issue | Venkat | Resolved | 2021-03-12 |  | Close | Mahesh will deploy on 12th Mar, Venkat to follow up and close | 16th Mar: Mail sent to parikshit to allow the Mumbai URL. Waiting for his response.
2021-03-11 | IM2888777 | CIS | 2021-03-05 | Attachment Drag and Drop | Venkat | Resolved | 2021-03-12 |  | Close | Check and explain the way it works, and close the ticket. | 12th Mar: Venkat has a call with Arpitha at 9:00 PM, post call he will take required action.
2021-03-11 | IM2888946 | KLI | 2021-03-05 | OTP Issue | Sweta | Resolved | 2021-03-12 |  | Close | Mahesh will deploy on 12th Mar, Venkat to follow up and close | 16th Mar: Mail sent to parikshit to allow the Mumbai URL. Waiting for his response.
2021-03-11 | IM2889499 | EFL | 2021-03-05 | P1 Ticket SMS to Manager/Lead Engineer | Venkat | Resolved | 2021-03-12 |  | Close | Three Follow ups are done, so close the ticket saying there is no response tomorrow | 12th Mar: Customer responded on 3rd Follow up, onboarding sheet sent to customer, cutomer to fill and send it back for configuration. 16th Mar: Two follow ups done after sending the onboarding sheet, customer yet to respond. 18th Mar: Venkat to update the resolution comments accordingly and close the ticket, as there is no reply after multiple followups.
2021-03-11 | IM2891345 | KAM | 2021-03-06 | Location Showing Default | Mohammed | Resolved | 2021-03-12 |  | Close | Check with mahesh, check with user, understand what is required, and get the ticket closed. | 12th Mar: Customer Confirmation Taken.
2021-03-11 | IM2893376 | KLI | 2021-03-08 | Unable to Update Security Questions, and Mobile Number on Self help portal. Not Getting OTP | Sweta | Resolved | 2021-03-12 |  | Close | Mahesh will deploy on 12th Mar, Venkat to follow up and close | 16th Mar: Mail sent to parikshit to allow the Mumbai URL. Waiting for his response. 18th Mar: Follow up and close the ticket. 19th Mar: Awaiting user confirmation for a screen sharing session as the customer is unable to change the Securty Questions. Sweta to talk to Mahesh and seek help
2021-03-11 | IM2894401 | RMC | 2021-03-08 | Bunge Ticket assgined to workgroup but not visible in the list. | Vignesh | Resolved | 2021-03-12 | 2021-03-15 | Close | Vignesh will check and close. | 12th Mar: Issue was when we were doing the duplicate workgroup cleanup. However, engineer needs time till Monday to confirm. Monday Vignesh to followup and close it.
2021-03-11 | IM2895039 | KLI | 2021-03-09 | OTP Issue | Sweta | Resolved | 2021-03-12 |  | Close | Mahesh will deploy on 12th Mar, Venkat to follow up and close | 16th Mar: Mail sent to parikshit to allow the Mumbai URL. Waiting for his response. 18th Mar: Follow up and close the ticket.
2021-03-11 | IM2895515 | KAM | 2021-03-09 | Unable to add new category, sub category, classification from Admin Module | Venkat | Resolved | 2021-03-12 |  | Check and Update | Check with Nagaraj K from Development team, take confirmation of whether it is pushed or when will it be pushed to production, accordinlgy take action. | 12th Mar: Action to check with Nagaraj is not done.
2021-03-11 | SR2895755 | Automation | 2021-03-09 | CMDB & KM Onboarding for SonicWall | Vignesh | Resolved | 2021-03-12 |  | Close | Onboard & Close | 12th Mar: Will be closed today
2021-03-11 | SR2896121 | TAGIC | 2021-03-09 | Data request. | Mohammed | Resolved | 2021-03-12 |  | Close | Provide data dump and close the ticket | 12th Mar: Data Provided to customer and ticket closed.
2021-03-11 | IM2897607 | Automation | 2021-03-10 | KLI Notifications not received | Vignesh | Resolved | 2021-03-11 |  | Close | Issue already resolved. Vignesh to close the ticket.
2021-03-11 | IM2897881 | EFL | 2021-03-10 | Auto ticket configuration to be done | Venkat | Closed | 2021-03-12 |  | Close | Configure and close.
2021-03-11 | IM2898033 | RMC | 2021-03-10 | On Reopen, Ticket is not cancelling the SLA and picking the new SLA if any details are changed post reopen. | Aravind | Resolved | 2021-03-12 |  | Close | Discuss, confirm and either close, or move to OH3P | 16th Mar: Follow up with Parameswar for the specific case as there is no issue, and the feature is working as per design.
2021-03-11 | SR2898920 | Automation | 2021-03-11 | Autoticket for cloudapp support | Aravind | Resolved |  |  |  | Aravind to Talk to Raghu and Provide an ETA by Tomorrow. | 12th Mar: We will close this ticket, once the new mailbox is ready and receiving alerts, a new ticket can be raised for this.
2021-03-11 | IM2899124 | KLI | 2021-03-11 | OTP Issue | Venkat | Resolved | 2021-03-12 |  | Close | Mahesh will deploy on 12th Mar, Venkat to follow up and close | 16th Mar: Mail sent to parikshit to allow the Mumbai URL. Waiting for his response. 18th Mar: Follow up and close the ticket.
2021-03-11 | IM2899426 | TAGIC | 2021-03-11 | User want's password to be reset | Venkat | Resolved | 2021-03-12 |  | Close | Check with the user if it is a EUP request. EUP is on AD Authentication, and we cannot reset the passoword. If it is for Engineer Portal, update the password from backend and close the ticket. | 12th Mar: Connectivity issue, did not close the ticket
2021-03-11 | IM2899520 | KLI | 2021-03-11 | No Receiving Email Notifications. | Vignesh | Resolved | 2021-03-12 | 2021-03-15 | Close | Address the issue and close the ticket. | 12th Mar: However, engineer needs time till Monday to confirm. Monday Vignesh to followup and close it. 16th Mar: Intemittent issue, we are seeking help from KLI, server connectivity goes down intermittently. 19th Mar: this is pending with RMC Network Team
2021-03-11 | IM2899550 | TAGIC | 2021-03-11 | User Access to be provided | Mohammed | Resolved | 2021-03-12 |  | Close | Awaiting customer confirmation. | 12th Mar: Access Provided, Customer Confirmed, and ticket closed.
2021-03-12 | SR2900432 | HMCL | 2021-03-12 | New SLA Notifications to be configured. | Aravind | On Hold (Customer) | 2021-03-18 | 2021-03-19 | Close | Configure and close. | 18th Mar: Aravind is on leave due to asset refresh, hence extended the deadline by 1 days to 19th Mar. 19th Mar: Details are not clear, sent back to customer for rectification and clarity. 23rd Mar: Mahaveer yet to provide the clarifications. He needs two to three more days for this. 24th Mar: Mahaveer yet to provide the clarifications. He needs two to three more days for this. Aravind to close this ticket, as king Mahaveer to get back with a new ticket when the required data is ready.
2021-03-12 | SR2900490 | Automation | 2021-03-12 | Bot user creation in Tata AIG | Aravind | Resolved | 2021-03-12 |  | Close | Action already completed, close the ticket
2021-03-12 | IM2900504 | HMCL | 2021-03-12 | HMCL Slowness Issue | Venkat | On Hold (Customer) | 2021-03-15 |  | Close | Move the ticket to on hold customer, Wait till Monday and close the ticket | 16th Mar: Issue reported again today, after server restart issue got resolved.
2021-03-12 | IM2900553 | CIS | 2021-03-12 | Ticket Response SLA is breached, why? | Mohammed | Resolved | 2021-03-15 |  | Close | All the tickets were not assigned to engineer, as at that point in time the system did not find an Online/Available engineer to assign, and manual assignment got delayed, hence it is breached. Pust this comment in the ticket and close the ticket. | 16th Mar: Mohammed is on leave, team doesn't have an update. Ticket yet to be closed.
2021-03-12 | IM2900564 | CIS | 2021-03-12 | Ticket is auto assigned, even if status is set to Meeting. | Sweta | On Hold (3rd Party) | 2021-03-15 | 2021-04-11 | Close | Get on to a call, test with the users for some time, then confirm and close the ticket. | 16th Mar: Availability dropdown setting back to Available status after changing it, in the new tabs which are being opened.
2021-03-12 | SR2900609 | HMCL | 2021-03-12 | New P1 SLA Notifications to be configured | Aravind | Resolved | 2021-03-18 |  | Close | Configure and close.
2021-03-12 | SR2900753 | HMCL | 2021-03-12 | New Request, if false alert resolution code is selected, it should ask to fill only 1 free test field instead of 3 free text fields. | Mohammed | Resolved | 2021-03-15 |  | Close | Feature is not feasible, close the ticket. | 16th Mar: Mohammed is on leave, team doesn't have an update. Ticket yet to be closed.
2021-03-12 | SR2900885 | HMCL | 2021-03-12 | Not able to change the Priority and category of the ticket | Venkat | Resolved | 2021-03-15 |  | Close | Venkat to arrange a call with HMCL, and close the ticket.
2021-03-12 | SR2901062 | CIS | 2021-03-12 | Department name has some special character in it, hence approval is not picking up. | Vignesh | Resolved | 2021-03-15 | 2021-03-16 | Close | Update the correct department name in requestor table, and confirm and close the ticket. | 16th Mar: Taking a lot of time than expected, hence moving the ticket to Vignesh. ETA also revised, from 15th to 16th. 18th Mar: Natarajan to help in closing this.
2021-03-12 | SR2901123 | Automation | 2021-03-12 | Bot rules configuration for Tagic | Aravind | Resolved | 2021-03-15 |  | Close | Configure and close.
2021-03-12 | SR2901175 | RMC | 2021-03-12 | New user onboarding. | Aravind | Resolved | 2021-03-15 |  | Close | Give access to users and close.
2021-03-16 | SR2901279 | SMC Automation | 2021-03-12 | Need to disable the duplicates rules. | Venkataramanaiah Katabathina | Resolved
2021-03-16 | SR2901347 | SMC Automation | 2021-03-12 | Adding Subcategory and classification details requested by Nupur | Venkataramanaiah Katabathina | Resolved
2021-03-16 | SR2901513 | SMC RMC | 2021-03-12 | Hi Aravind and team I need the attached configurations highlighted green to be added for Enzen SGN Account. Please consider it as an urgent request since the Go live for the account is on 15th Mar '21. Note : For SR please disable the existing customer mapping categorySubcategory details and update with the one i have updated in the attached SMC on boarding sheet. Call me on 8277608668 for any queries. Regards Maya J Mathew | Aravindsagar Venkatesh | Resolved
2021-03-16 | SR2901725 | SMC RMC | 2021-03-13 | Please remove me from JUB SMC notifications. | Venkataramanaiah Katabathina | Resolved
2021-03-16 | IM2901798 | SMC HMCL | 2021-03-13 | Dear Team Today we have not received daily reports please check at your end. Example : 1 DPCR 2 EUP P1 3 Daily ageing Regards Sangita Rani | mohammed inayathulla | Resolved
2021-03-16 | SR2901945 | SMC Automation | 2021-03-13 | Generate O365 Invoice from admin login of O365 and share with finance team AmitDeA1@microland.com | mohammed inayathulla | Resolved
2021-03-16 | SR2902206 | SMC New KGI | 2021-03-13 | hi team i an gaving admin rigts access but still unabld to access admin tab showing below error id :- GV0146 | mohammed inayathulla | Resolved
2021-03-16 | IM2902264 | SMC KLI | 2021-03-13 | Unable to remove user name - Jeyakumar ACNewton KAKLI Employee ID: OM33870 from SMC asset tag No. KLI21450 Please resolve the issue. | Venkataramanaiah Katabathina | Resolved
2021-03-16 | IM2902265 | SMC KLI | 2021-03-13 | Unable to remove user name - Gyanendra Verma Tied KLI Employee ID: OM32080 from SMC asset tag No. KLI08666 Please resolve the issue. | Venkataramanaiah Katabathina | Resolved
2021-03-16 | IM2902267 | SMC KLI | 2021-03-13 | Unable to remove user name - Thomas Joseph Alternate KLI Employee ID: OM5834 from SMC asset tag No. KLI29660 Please resolve the issue. | Venkataramanaiah Katabathina | Resolved
2021-03-16 | IM2903453 | SMC New TAGIC | 2021-03-15 | Dear SMC Team unable to download call dump since morning Please check update. | mohammed inayathulla | Resolved
2021-03-16 | IM2903515 | SMC RMC | 2021-03-15 | Unable to resolve the ticket SR2901341 PFA | Venkataramanaiah Katabathina | Resolved
2021-03-16 | SR2903570 | SMC HMCL | 2021-03-15 | Dear Team Please Update the below listed user details in Smart Center. They are newly joined in organization and unable to raise tickets in the Smart Center. | Venkataramanaiah Katabathina | Resolved | 2021-03-16 |  | Close | Configure and close
2021-03-16 | SR2903842 | SMC UCFS | 2021-03-15 | How come response is 30 mins and resolution 15 mins for P1 | mohammed inayathulla | Resolved |  |  |  |  | 16th Mar: Mohammed is on leave, team doesn't have an update. Ticket yet to be closed.
2021-03-16 | SR2903843 | SMC HMCL | 2021-03-15 | Hi Team We need Smart Center Mobile numbers data which we are using for SMS alert for engineers ticket assignment. If you need any more clarification please let me know. | mohammed inayathulla | Resolved
2021-03-16 | SR2903930 | SMC Automation | 2021-03-15 | RE: TSE - DaaS - Smartcenter access | Venkataramanaiah Katabathina | Resolved
2021-03-16 | SR2904078 | SMC CIS | 2021-03-15 | Hi Saif PFA image for reference as I am not able to raise the ticket. It seems it requires the approval. For more PFA | Venkataramanaiah Katabathina | Resolved | 2021-03-15 |  | Close | Looks like a understanding issue, explain and close
2021-03-16 | SR2904185 | SMC Automation | 2021-03-15 | Need to unlock the KLI helpdesk | Venkataramanaiah Katabathina | Resolved
2021-03-16 | SR2904272 | SMC RMC | 2021-03-15 | Hi Team Im unable to login please reset my password Suraj R | mohammed inayathulla | Resolved
2021-03-16 | IM2904348 | SMC New EFL | 2021-03-15 | Hi Team Following ticket's status is not changed. pls. check on urgent basic. IM2904173 | Venkataramanaiah Katabathina | Resolved
2021-03-16 | IM2904497 | SMC KLI | 2021-03-15 | Unable to remove user name - Vijay Rangle ML IT KLI Employee ID: CMS1894 from SMC asset tag No. KLI21335 Please resolve the issue. | Venkataramanaiah Katabathina | Resolved
2021-03-16 | IM2904501 | SMC KLI | 2021-03-15 | Kindly check as we are not able to assign user name - Amitoz Singh Tied KLI Employee ID: OM107967 in below asset tag Laptop KLI35452 5HD4L13 KLI - Mumbai - Kotak Infinity – HO | Venkataramanaiah Katabathina | Resolved
2021-03-16 | SR2904627 | SMC Automation | 2021-03-15 | Mohammed Hi Aravind Thank you for stopping the SR status notifications emails . I have asked Mohammed K from your team to stop the ‘Open’ and ‘Assigned’ notification for Incident tickets also now on priority. Since all tasks from TFSnow first create as an Incidents first in SMC and its trigger mails open and assigned before converting to SR. Regards Maya J Mathew | mohammed inayathulla | Resolved
2021-03-16 | SR2904708 | SMC Automation | 2021-03-15 | Hi Can you help me to get data from SmartCenter for HDU ticket from Jan 2021 onward? Warm Regards Shailesh Lonare | mohammed inayathulla | Resolved
2021-03-16 | SR2905188 | SMC New TAGIC | 2021-03-16 | Hi SMC Team Request you to rectify below mentioned identified gaps. The ticket details for each gaps are pasted in separate sheets for reference. 1. REQUESTOR NAME blank – 13 2. Location Blank – 89 3. SLA not defined – 12 4. Resolution code blank -412 mobile number: 7045894769 | mohammed inayathulla | On Hold (Customer) |  |  |  |  | 16th Mar: Mohammed is on leave, team doesn't have an update. Ticket yet to be closed. 18th Mar: Mohammed to check today and give an update. 19th Mar: Work is in progress, need to close ASAP. 23rd Mar: As per data shared it is updated, rest awaiting data to configure and close. 24th Mar: Third follow up is also done, ticket to be closed via three strike rule.
2021-03-16 | SR2905193 | SMC New TAGIC | 2021-03-16 | Dear Team Please include new approver in the Server Commission Decommission approvers list on SMC. Include him in both Level 1 level 2 approval list. Yogesh Lawale - Yogesh6.Lawale@tataaig.com | Sweta Saran | Resolved | 2021-03-16 |  | Close | Configure and close
2021-03-16 | IM2905529 | SMC RMC | 2021-03-16 | Hi Team The numbers and SLA attainment for Enzen NGN is incorrect on the automated dashboard. The below changes to be incorporated: For Enzen NGN Incidents with P5 Priority should be considered as Service Requests The actual service requests raised SR with any priority should be considered as Change Management tickets. Requesting to incorporate the changes mentioned above so that the SLA attainment and the numbers would show up apprioriately. Warm regards Harry | Venkataramanaiah Katabathina | Resolved |  |  | Close | Incident cannot be considered as SR, it needs to be Converted to SR by engineer once the ticket is raised. For SR, a change ticket needs to be created manually by the Engineer, and the SR ticket will mobe to On Hold (Change). Once the change is closed, the SR will be moved automatically to Work in Progree. This is as per the system design, and process must be followed accordingly.
2021-03-16 | SR2905592 | SMC Automation | 2021-03-16 | Oreta - MMSG Unity Bio Nokia - Indosat Mott MacDonald GCC AbInBev Bunge | Vignesh Annadurai | Resolved | 2021-03-19 |  |  |  | 18th Mar: Vignesh is doing the CMDB and KM configurations
2021-03-16 | SR2905753 | SMC CIS | 2021-03-16 | i have arequested for laptop replacement but the approval is sent for my previous assigned manager while i was in RDP Thejas babubut not the current one Raja Ravi ... so the approval needs to be sent to Raja ravi. | Sweta Saran | Resolved | 2021-03-16 |  | Close | Manage ID not updated in Asset_Users table. Mahesh to check the AD Sync application.
2021-03-16 | IM2905796 | SMC New TAGIC | 2021-03-16 | Hi Team We are received emails on Email2Ticket@tataaig.com mailbox but ticket was not generated. Kindly check on high priority. | Sweta Saran | Resolved | 2021-03-16 |  | Close | Araving will help if required.
2021-03-17 | IM2905934 | SMC New KGI | 2021-03-16 | hi team there may be some issues while fetching report old data showing there may be some issue in date format | Venkataramanaiah Katabathina | Resolved
2021-03-17 | SR2906168 | SMC RMC | 2021-03-16 | Hi Team Please provide Enzen SGN account access also to NarendraM@microland.com. Base workgroup RMC Citrix Note : He is an existing SMC user. Regards Maya MJ | Venkataramanaiah Katabathina | Resolved
2021-03-17 | IM2906237 | SMC RMC | 2021-03-16 | Critical : Less ticket closures ! 315 - Dashboard not updating | Mohammed Inayathulla | Work In Progress |  |  |  |  | 18th Mar: Mohammed to Connect with Ajay and figureout what is the exact problem, Vignesh's help might be required here. 19th Mar: It is an ElasticSearch dashboard. Mohammed to coordinate with Utkal, Satya, and Bindu and get this addressed. 23rd Mar: Mohammed to talk to Utkal and Ajay, schedule a call to get this addressed. 24th Mar: Mohammed has got the required clarity from Utkal, the same to be explained to Ajay. Basically there were workgroups removed from the Dashboard which were given by Manjunath Kalal, from the report if we remove these workgroups, the numbers are matching with the numbers on Dashboard, same to be explained to Ajay. For further report/dashboard related queries, Ajay to talk to Manjunath Kalal.
2021-03-17 | IM2906416 | SMC RMC | 2021-03-16 | Can you update the details for this below user - Database@enzen.com Need to update First name last name current contact etc | Venkataramanaiah Katabathina | Resolved
2021-03-17 | SR2906446 | SMC RMC | 2021-03-16 | Hi Team Please create a new workgroup named ' RMC - Tools Enzen SGN'. This is particularly for Enzen SGN account . Please call me for any clarification or any more details require. Regards Maya MJ | Aravind | Resolved |  |  |  |  | 18th Mar: Natarajan asked for additional information to approve this workgroup creation. 19th Mar: Aravind has explained to Maya, and waiting from confirmation.
2021-03-17 | IM2906803 | SMC RMC | 2021-03-17 | Hi Please check on this issue where in Chandrakanth is unable to login to SMC portal even after multiple password resets. The error says that the id or password is incorrect. Please look into this on priority once you login for the day. He had access to the portal before. PFA | mohammed inayathulla | Resolved
2021-03-17 | SR2907099 | SMC RMC | 2021-03-17 | Unable to close Task TSK2825182 - IM2761549 | Sweta Saran | Resolved
2021-03-17 | SR2907341 | SMC RMC | 2021-03-17 | Add Devices in SC - MLCIS | Sweta Saran | Resolved | 2021-03-19 |  |  |  | 18th Mar: CMDB is enabled for MLCIS, hence this needs to be handled accordingly.
2021-03-17 | IM2907352 | SMC KLI | 2021-03-17 | Unable to remove user name - Karthikeyan K KA KLI Employee ID: OM35020 from SMC asset tag No. KLI34821 Please resolve the issue. | mohammed inayathulla | Resolved
2021-03-17 | SR2907464 | SMC HMCL | 2021-03-17 | Need to be remove email id from below reports. itsd.hotl@heromotocorp.com . 1 SD Weekly Performance Report 2 Daily CSD performance report | Sweta Saran | Resolved | 2021-03-19 |  |  |  | 18th Mar: Change the configurations and close. 19th Mar: Work is in progress This will be closed today.
2021-03-17 | SR2907476 | SMC HMCL | 2021-03-17 | Need to be remove Cancelled tickets from the report Number is : RP000392 | mohammed inayathulla | Resolved
2021-03-17 | SR2907493 | SMC RMC | 2021-03-17 | UREGNT UPDATE NEEDED : Smart Center Access | Venkataramanaiah Katabathina | Resolved
2021-03-17 | SR2907504 | SMC RMC | 2021-03-17 | Hi Team I need the list of members in RMC Collaboration queue who has access to Enzen SGN account Regards Maya MJ | Venkataramanaiah Katabathina | Resolved
2021-03-17 | SR2907542 | SMC RMC | 2021-03-17 | Hi team Please delete the SR2907281 from backend. Regards Maya J Mathew | Sweta Saran | Resolved
2021-03-17 | IM2907560 | SMC New Nokia | 2021-03-17 | RE: Urgent P3 - Cannot login to SMC | Sweta Saran | Resolved
2021-03-17 | IM2907562 | SMC CIS | 2021-03-17 | Hi Team One of the VIP user has raised a ticket but on ticket under VIP user field it display as no Attached is the VIP user list please have it updated if there is mismatch in VIP user list. | mohammed inayathulla | Resolved
2021-03-17 | SR2907778 | SMC Automation | 2021-03-17 | SMC - Summit Analysis details to Summit Team | Vignesh Annadurai | Resolved | 2021-03-19
2021-03-17 | SR2907789 | SMC Automation | 2021-03-17 | Remove Arun Ravi as a approver from KM Module approval list for HDU customers | Vignesh Annadurai | Resolved
2021-03-17 | SR2907834 | SMC Automation | 2021-03-17 | Cloud App Support -- Enable clock only for 9*5 support 9 AM to 7:30PM Stop clock at 7:30PM and enable at again next day morning 9AM. Saturday and Sunday clock needs to be stopped | Mohammed Inayathulla | Resolved
2021-03-17 | SR2908008 | SMC Automation | 2021-03-17 | Remove Mandatory option on Category subcategory classification fields on KM - Owner – Vignesh . – Deadline – Tomorrow EOD. |  | Resolved | 2021-03-19
2021-03-17 | SR2908032 | SMC Automation | 2021-03-17 | Automated Report 17th Aug | Sweta Saran | Resolved
2021-03-17 | SR2908147 | SMC RMC | 2021-03-17 | SR2907482 | Venkataramanaiah Katabathina | Resolved
2021-03-17 | SR2908195 | SMC RMC | 2021-03-17 | RE: Remove Enzen SGN account view for HDU Shared Collab team firstName lastName email Ravi Raj RaviRa12@microland.com Chandrakant L T_ChandrakantL@microland.com | Venkataramanaiah Katabathina | Resolved
2021-03-17 | SR2908227 | SMC RMC | 2021-03-17 | Hi Team Please disable Enzen SGN account view for below users. Please call me for any query. firstName lastName email Divya S DivyaS12@microland.com Snehal Menezes SnehalMM@microland.com Senthil MA SenthilMK@microland.com Amodini Singh amodinisi@microland.com Subhodeep Dasgupta SubhodeepDa1@microland.com Regards Maya j Mathew | Venkataramanaiah Katabathina | Resolved
2021-03-17 | IM2908547 | SMC CIS | 2021-03-18 | Hi Team Please raise ticket assign it to RMC messaging team as we are not receiving emails to our Microland email IDs. Even When we send emails from Microland email ID to External domain ex.omc.duty.managers@serco.com not receiving email. Messaging team has updated A: As per the message trace in Iron port we see that the particular email which user have not received has not reached the GatewayIronPort. However the other emails from the same sender email id or IP address is delivered to recipient. So we have requested the application team to check the logs at application end as we will be able to track the email only after it hits our Gateway. Can this be checked on priority basis Regards Santhosh Kumar Mobile:91 9620075138 USACanada: 1 908 293 8185 Extn-1 UK: 44 0 203 564 7812Extn-1 | Mohammed Inayathulla | Resolved | 2021-03-18 |  |  | This is not a SMC Support ticket, needs to be removed from our bin. If required, we can even delete the ticket from backend.
2021-03-17 | IM2908568 | SMC CIS | 2021-03-18 | @RMC Messaging Team: Emails are not delivering to the email domain @serco.com @sungardas.com from the application hosted on the Azure Server - 172.21.7.11 using ob1.hc2993-97.iphmx.com to relay emails Messaging team has updated Ple ase route back the ticket once the Application team share the logs so that we can proceed with further troubleshoot. The same has been discussed in Conference call as well . refer the attachments for more details. Please check this check on priority. and up date us | Sweta Saran | Resolved
2021-03-17 | IM2908573 | SMC CIS | 2021-03-18 | @RMC Messaging Team: Emails are not delivering to the email domain @serco.com @sungardas.com from the application hosted on the Azure Server - 172.21.7.11 using ob1.hc2993-97.iphmx.com to relay emails Messaging team has updated Please route back the ticket once the Application team share the logs so that we can proceed with further troubleshoot. The same has been discussed in Conference call as well . refer the attachments for more details. Please check this check on priority. and up date us Veeresh | Sweta Saran | Resolved |  |  |  |  | 19th Mar: awaiting customer confirmation. 23rd Mar: Sweta has done 3rd Follow UP today, she will close it today EoD
2021-03-17 | SR2908748 | SMC New CIS | 2021-03-18 | Hi Team Please check and let us know with whom this approval is pending APR2885893 | Mohammed Inayathulla | Resolved
2021-03-17 | SR2908753 | SMC New CIS | 2021-03-18 | Hi Team Please provide access to list of BUHR's to performance management workgroup. Please note only performance management workgroup access must be given to them and no other workgroups. List will be shared over mail | Venkataramanaiah Katabathina | Resolved | 2021-03-18
2021-03-17 | IM2908974 | SMC RMC | 2021-03-18 | Hi Aravind As discussed For Enzen SGN when we convert IM to SR the 'Assigned to Me' button was missing' for SR ticket please check and enable the option. Regards MayaMJ | Aravindsagar Venkatesh | Resolved | 2021-03-19 |  |  | Vignesh to check and updated. | 19th Mar: Aravind to check and revert on whether the issue really exists.
2021-03-17 | SR2908977 | SMC RMC | 2021-03-18 | Hi Team Requesting to provide access to CMDB tab on SMC for the below users: Harry S HarryS1@microland.com Jithu J JithuJR@microland.com Dilip M DilipMY@microland.com Sunil S Reddy SunilS1@microland.com Ashokkumar Gunasekaran AshokkumarGu@microland.com Sharad Shekhar SharadS@microland.com This access to CMDB tab is required to update assets on SMC upon commissioning and decommissioning. Requesting to process the request at the earliest possible. Warm regards Harry | Sweta Saran | Resolved | 2021-03-19 |  |  | Provide the required access and close this. | 19th Mar: Work is in progress This will be closed today. 23rd Mar: Vignesh to help and Sweta to provide the access
2021-03-17 | SR2908981 | SMC CIS | 2021-03-18 | Hi Team Is anyone looking into this please?? I just raised another ticket APR2811430 and it still ends up going to my previous RM. Amith AmithDC@microland.com Please change the Amith RM as Vinay kundur. | Mohammed Inayathulla | Resolved | 2021-03-18 |  |  | Talk to Mahesh, get it closed today. | 19th Mar: Yet to follow up with Mahesh, please close it today.
2021-03-17 | IM2908996 | SMC KLI | 2021-03-18 | Unable to remove user name - Gourav Sinha Alternate KLI Employee ID: OM14512 from SMC asset tag No. KLI25145 Please resolve the issue. | Venkataramanaiah Katabathina | Resolved
2021-03-17 | SR2909041 | SMC RMC | 2021-03-18 | Hi Team Please enable Automated dashboards for MohammedAs12@microland.com and SanjivkumarGJ@microland.com Regards Maya MJ | Venkataramanaiah Katabathina | Resolved | 2021-03-18 |  |  | Venkat to talk to Maya and close this today.
2021-03-17 | IM2909280 | SMC RMC | 2021-03-18 | Hi Team raising ticket on behalf of user Balachandran B. Issue : User gets error while opening mail notification. PFA mail for reference Regards Maya MJ | Mohammed Inayathulla | Resolved | 2021-03-19 |  |  | Mohammed to discuss with Natarajan for this. | 19th Mar: Check with user about specific ticket details where he is having this issue / problem
2021-03-17 | SR2909313 | SMC HMCL | 2021-03-18 | Please add Maventic as a Vendor in SmartCenter | Venkataramanaiah Katabathina | Resolved
2021-03-17 | SR2909343 | SMC RMC | 2021-03-18 | Urgent Enable Jubilant Pharma SMC access to PremR@microland.com | Venkataramanaiah Katabathina | Resolved | 2021-03-18 |  |  | Ask customer to use the admin module.
2021-03-17 | IM2909429 | SMC KLI | 2021-03-18 | Not Able to remove the user name in assignment tab kindly raised one ticket for this issue. AssetTag-KLI18545 | Vignesh | Resolved | 2021-03-19 |  |  | Vignesh to help, must be something related to configuration. | 19th Mar: Vignesh to check with Dev team. In cloud it is working as expected, in KLI it is successful but it is not actually working.
2021-03-19 | SR2909531 | SMC KLI | 2021-03-18 | Please raised ticket to remove this user name Ashish Garg in assign tab against each asset tag Employee ID EntityType Asset Tag Serial Number OM30408 TFT Monitor KLI10612 AOCVM5D73901154 OM30408 Switch KLI10979 F30H474003033 OM30408 KLI Printer KLI11101 VNRJ79V01D OM30408 Switch KLI14824 F306385018501 OM30408 Scanner KLI20575 CN33KA104W OM30408 UPS - Standalone KLI21952 1081077-23706725 OM30408 Router KLI27728 FGL211991FP OM30408 Projector KLI28476 PDR5H0087804E OM30408 CPU KLI30053 UXB1JSIZ08I2037758 OM30408 Laptop KLI30846 8V7SNQ2 OM30408 UPS - Standalone KLI31580 B21822010719 OM30408 Scanner KLI33255 52834435 OM30408 Scanner KLI33314 52834430 OM30408 Router KLI33750 FGL230911P1 | Venkataramanaiah Katabathina | Resolved
2021-03-19 | SR2909558 | SMC RMC | 2021-03-18 | Smart center access for Jubilant Citrix Infra | Sweta Saran | Closed | 2021-03-19
2021-03-19 | SR2909596 | SMC RMC | 2021-03-18 | Approval to provision access for MLRMC smart center Enzen. | Mohammed Inayathulla | Resolved
2021-03-19 | SR2909621 | SMC KLI | 2021-03-18 | Need some changes in techassist auto generated mail opened by you on hold customer on hold 3rd party resolved and closed there should be no option of reply reply all and forward. And there will be message saying that this is system auto generated mail don’t reply back and update the requested information in techassist | Mohammed Inayathulla | On Hold (Customer) |  |  |  |  | 19th Mar: Ticket will be closed by 22nd Monday EOD 24th Mar: Clarification is already provied by Natarajan, moreover there is no reponse after three stikes, so we will close this ticket today.
2021-03-19 | SR2909630 | SMC RMC | 2021-03-18 | Smartcentre Slowness Degrade in performance | Venkataramanaiah Katabathina | Resolved |  |  |  |  | 19th Mar: customer call scheduled at 07.00 PM Today
2021-03-19 | IM2909750 | SMC KLI | 2021-03-18 | Unable to remove user name - Praduman Yadav Tied KLI Employee ID: OM22811 from SMC asset tag No. KLI28409 Please resolve the issue. | Venkataramanaiah Katabathina | Resolved
2021-03-19 | SR2909767 | SMC TAGIC | 2021-03-18 | Tagic Report | Sweta Saran | Resolved
2021-03-19 | SR2909979 | SMC RMC | 2021-03-18 | RE: SMC access required for Enzen SGN. PFA Created by Subhodeep | Mohammed Inayathulla | Resolved
2021-03-19 | IM2910128 | SMC CIS | 2021-03-19 | Amitabh Shukla Need one help...I have a contractor here login id I_jaimess he is trying to reset his ad password on ADSS but there is no OTP option...it just give security question option then gets stuck pleas do the needful refer the attachment for the error screen shot. | Mohammed Inayathulla | Work in Progress |  |  |  |  | 19th Mar: Recent Not yet started to work 23rd Mar: Mohammed to check with Mahesh and get this addressed. 24rd Mar: Mohammed to check with Mahesh and get this addressed.
2021-03-19 | IM2910343 | SMC KLI | 2021-03-19 | Kindly check as we are not able to assign below assets on user name - Abhishek H Mishra Tied KLI employee id - OM107429 CPU KLI29003 UXB1JSIN57H4935844 TFT Monitor KLI25481 MMT3FSS001613009203B00 | Sweta Saran | Closed
2021-03-19 | SR2910355 | SMC HMCL | 2021-03-19 | Need to be add the email ID : rajkumar.nagaiah@heromotocorp.com in below report and remove name HO from report. Pending Call Report for AOHOZO | Venkataramanaiah Katabathina | Work in Progress |  |  |  |  | 19th Mar: Will be closed by 22nd Monday EOD 23rd Mar: Vignesh to check with Venkat and update. 24th Mar: Email is added, HO Workgroup to be removed. Mahesh to remove and confirm.
2021-03-19 | SR2910360 | SMC HMCL | 2021-03-19 | Dear Team Kindly add Itsd.areaoffice@heromotocorp.com Id in below reports. Daily Pending Call Report for AOHOZO 17 Report Daily Pending Call Report for Workaround Provided And create New report for Daily Pending Call Report for HM5V and it should be trigger to below mention mails ID's. itsd.pm@heromotocorp.com itsd.csdtl@heromotocorp.com itsd.om@heromotocorp.com chandrashekhar.baghel@heromotocorp.com rajkumar.nagaiah@heromotocorp.com itsd.cptl@heromotocorp.com itsd.cp@heromotocorp.com itsd.cpac@heromotocorp.com | Venkataramanaiah Katabathina | Work in Progress |  |  |  |  | 19th Mar: Will be closed by 22nd Monday EOD 23rd Mar: Vignesh to check with Venkat and update. 24th Mar: Email changes are done, new report to be created.
2021-03-19 | SR2910371 | SMC HMCL | 2021-03-19 | Need to be create a report for new HM6C Plant location it's very urgent. Report name should be as : Daily Pending Call Report for HM6C. Email Add : itsd.cp@heromotocorp.com itsd.cptl@heromotocorp.com rajkumar.nagaiah@heromotocorp.com itsd.qc@heromotocorp.com itsd.csdtl@heromotocorp.com itsd.om@heromotocorp.com | mahesh k | Work in Progress |  |  |  |  | 23rd Mar: This will take time, we already have a lot of items in our plate.
2021-03-19 | SR2910410 | SMC Automation | 2021-03-19 | Please check today's automated report | Mohammed Inayathulla | Resolved
2021-03-19 | IM2910461 | SMC CIS | 2021-03-19 | Hi Team I am unable to pull the asset dump from past two days . Can you check on this priority also please share me the asset dump immediately. We have a review today required on high priority RP000326 Regards Suvarna K | Mohammed Inayathulla | Resolved
2021-03-19 | IM2910469 | SMC New EFL | 2021-03-19 | Hi Team Please check user is not able to reset password through AD self service portal. getting error you have exceeds the maximum try limit please try after sometimes. and after sometime its is not getting reset. Password reset link: https:adselfservice.eurekaforbes.co.inAccountLogOn | Mohammed Inayathulla | Work in Progress |  |  |  |  | 19th Mar: Checking with Mahesh 23rd Mar: Mahesh needs server access to check on the EFL ADSS Database. 24th Mar: Mahesh needs server access to check on the EFL ADSS Database.
2021-03-19 | IM2910543 | SMC New EFL | 2021-03-19 | Hi Team There is one ask on addition on column for “Reopened Tickets” to “EFL- RP001 - Incident and Service request SLA dump” report to check which tickets are reopened before Ticket closed. Please raise ticket to SMC team to enable column for “Ticket Reopened?” in the above mentioned report. This is required to calculate FCR metric. | Venkataramanaiah Katabathina | Resolved
2021-03-19 | IM2910605 | SMC RMC | 2021-03-19 | Hi team 1. The last manual update time is not proper for few tickets in 'RP000105'. Please check immediately and sort it. IM2906300 IM2904989IM2904089IM2906395SR2906270IM2904089 IM2904989 2. Also when you open an Incident page in SMC the 'Recent Update time' on top Bar it should ideally be showing the recent activity update time but its same as issue as above it not showing the proper recent update date and time. have given the snapshot for your reference. Please fix it. Call me for any queries. Regards Maya J Mathew | Aravindsagar Venkatesh | Work In Progress |  |  |  |  | 19th Mar: New Requirement will Discuss with Natarajan. 23rd Mar: Seems to be a bug, need to fix.
2021-03-19 | IM2910671 | SMC KLI | 2021-03-19 | Dear Team I am not receiving any emails from Technology Support desk kli.tsd2@kotak.com whenever I raise a Ticket in IT. Please check and correct the same as I am unable to see any updates on my tickets. solanki.jagruti@kotak.com - LE92802 | Sweta Saran | Resolved
2021-03-19 | SR2910790 | SMC RMC | 2021-03-19 | Apotex Tracker 03-02-2021M | Vignesh | Work in Progress |  |  |  |  | 19th Mar: Vignesh will Discuss with Natarajan 23rd Mar: Vignesh to check on this and give an update to customer, as to whether the tickets are genuine or not. 24th Mar: Vignesh to check on this and give an update to customer, as to whether the tickets are genuine or not. This will be done by or before 26th Mar
2021-03-19 | SR2910827 | SMC RMC | 2021-03-19 | Hi AravindNatarajan As discussed today please enable an auto rule to convert the mail with the Subject ‘ TASK' 'RITM ‘ to create and SR tickets than creating default Incident tickets. Please let me know how soon we can enable this feature. Regards Maya J Mathew | Aravindsagar Venkatesh | Resolved
2021-03-23 | SR2911052 | SMC New CIS | 2021-03-19 | Hi Team The below employee is from GE SBU. His department is reflecting as HR. Please check and update on it. Employee id= 22590 Employee name= Pankaj Dhakad Please confirm once done. | Venkataramanaiah Katabathina | Resolved
2021-03-23 | IM2911072 | SMC KLI | 2021-03-19 | Unable to remove user name - Durgadevi Mudaliyar FMG KLI Employee ID: OM74865 from SMC asset tag No. KLI31513 Please resolve the issue. | Venkataramanaiah Katabathina | Closed
2021-03-23 | IM2911078 | SMC KLI | 2021-03-19 | Unable to remove user name - Durgadevi Mudaliyar FMG KLI Employee ID: OM74865 from SMC asset tag No. KLI31575 Please resolve the issue. | Venkataramanaiah Katabathina | Closed
2021-03-23 | IM2911083 | SMC KLI | 2021-03-19 | Unable to remove user name - Durgadevi Mudaliyar FMG KLI Employee ID: OM74865 from SMC asset tag No. KLI31577 Please resolve the issue. | Venkataramanaiah Katabathina | Closed
2021-03-23 | IM2911199 | SMC HMCL | 2021-03-19 | Unable to Problem ticket against this Incident IM2898740 please support | Sweta Saran | On Hold (Customer) |  |  |  |  | 23rd Mar: HMCL Team to share the category subcategory information for the PM ticket for the service line PLM Support. 24th Mar: Customer yet to get back with the data.
2021-03-23 | IM2911236 | SMC New EFL | 2021-03-19 | Hi Team Please replicate all the access of RaiduRaM to new employee YuvarajG provide all the ticket notification access to new employee. | Mohammed Inayathulla | Closed
2021-03-23 | SR2913186 | SMC New CIS | 2021-03-21 | Hi Team The response sla and resolution sla time on the HR dashboard does not freeze on weekends and after 6.30 pm on weekdays. Please look into this. This impacts our SLA | Mohammed Inayathulla | Resolved |  |  |  |  | 23rd Mar: Yet to get the sample tickets from the HR Team.
2021-03-23 | SR2913513 | SMC RMC | 2021-03-22 | Re: Bedminster OU SR2905110 PFA Created by Subhodeep | Sweta Saran | Resolved |  |  |  |  | 23rd Mar: This is not an issue, this is how the system works, which needs to be explained by Sweta to the enginer. Once approval is completed, he will be able to see the Resolve button.
2021-03-23 | SR2913736 | SMC Automation | 2021-03-22 | RE: Forms Creation in the End User Portal. | Aravindsagar Venkatesh | Resolved
2021-03-23 | IM2913891 | SMC Automation | 2021-03-22 | Unable to login to the HelpDesk | Venkataramanaiah Katabathina | Resolved
2021-03-23 | SR2913982 | SMC New CIS | 2021-03-22 | APR2904435 requires an approval but I don’t see any approval matrix. Without Approval Matrix how the ticket is converted into APR. Can you please fix this issue and assign this ticket to NiroopL@microland.com for Approval. | Venkataramanaiah Katabathina | Resolved
2021-03-23 | IM2913987 | SMC New CIS | 2021-03-22 | Unable to raise ticket to Hubbler sub category. If we select category as Microland application and sub category as Hubbler it is showing Failure | Sweta Saran | Work In Progress |  |  |  |  | 23rd Mar: Asked user for a screensharing session we are unable to replicate the issue, awaiting. 24th Mar: We are able to replicate the error
2021-03-23 | SR2914048 | SMC KLI | 2021-03-22 | We have created category and subcategory as per attached mail. Please set the priority and impact as per attached mail Type : Service Request Category - PS Connect existing sub category of ticket - KB code update Priority – SR3 Medium | Sweta Saran | Resolved
2021-03-23 | SR2914058 | SMC CIS | 2021-03-22 | Hi Team Muniraja is unable to login to below linkportal using his credentials received credentials error https:smartcentersupport.microland.comAccountLogonsmccis Please check confirm if ID is disabled or share the credentials to login | Venkataramanaiah Katabathina | Resolved
2021-03-23 | IM2914075 | SMC Automation | 2021-03-22 | Hi Team The employee s department is changed but it is not reflecting on Ask Microland. This has impacted the leave reversal process. Please check and update the same. Also let us know is the sync of department done from AD? MONICA S | Mohammed Inayathulla | Resolved
2021-03-23 | SR2914097 | SMC Automation | 2021-03-22 | Hi Venkat Smart Center team Only laptop serial number is uploaded User details is not uploaded could you please upload and confirm ASAP Thanks Best Regards Pavithra R | Mohammed Inayathulla | Resolved
2021-03-23 | SR2914152 | SMC RMC | 2021-03-22 | Hi Team Can you please provide access for SmartOps and SmartCentre for Madhuri and Geetha. SmartCentre support- please map user with same access as Manjunath Kalal https:rmcops.microland.comAccountmicroland KushbooArdra- please provide Smart Ops access to Madhuri and Geetha for all HDU shared https:adfs01.microland.comadfsls?wa=wsignin1.0wtrealm=https3a2f2fsmartops.microland.comwctx=rm3d026id3dpassive26ru3d252fGovernanceCockpit252fwct=2021-03-19T053a033a55Z Thanks Joseph | Sweta Saran | Resolved
2021-03-23 | SR2914159 | SMC Automation | 2021-03-22 | add procurement in “Admin Finance Helpdesk” section highlighted - requested by Muniraja | Vignesh Annadurai | Resolved
2021-03-23 | SR2914186 | SMC HMCL | 2021-03-22 | Dear Team Kindly update the attached listed user details in Smart Center. They all are recently joined and unable to raise their ticket. Regared's Roojvelt | Venkataramanaiah Katabathina | Resolved
2021-03-23 | SR2914297 | SMC Automation | 2021-03-22 | Test ticket by SmartCenter support team. | Aravindsagar Venkatesh | Resolved
2021-03-23 | SR2914381 | SMC New TAGIC | 2021-03-22 | Hi Team Please reset password for below id in Smartcenter Nemehta Mo Number : 9022368167 | Sweta Saran | Resolved
2021-03-23 | SR2914455 | SMC RMC | 2021-03-22 | Hi Sweta Team Please provide Admin module access in RMCOPS https:rmcops.microland.com to below resources. PARTHU CHITTAMURU PARTHUC@microland.com Umashankar Balan UmashankarBa@microland.com Sumedh Bhalerao SumedhBN@microland.com These are new joiners in Shift Manger Team. Please clone their ID’s with the same access as PramodPk@microland.com | Venkataramanaiah Katabathina | Resolved
2021-03-23 | SR2914497 | SMC Automation | 2021-03-22 | Hi SMC Team Can you share the list of team members who are part of RMC tools group for Enzen SGN ? Post that I will check and share the list who doesn’t require access. | Mohammed Inayathulla | Resolved
2021-03-23 | IM2914680 | SMC KLI | 2021-03-22 | Unable to remove user name - Mausam Pandya Central Ops KLI Employee ID: OM84431 from SMC asset tag No. KLI29334 Please resolve the issue. | Sweta Saran | Resolved
2021-03-23 | SR2914767 | SMC RMC | 2021-03-22 | Adding All Menabev CI to SMC | Venkataramanaiah Katabathina | Resolved
2021-03-23 | SR2914834 | SMC Automation | 2021-03-22 | Need to verify the Reports | Venkataramanaiah Katabathina | Resolved
2021-03-23 | SR2914874 | SMC Automation | 2021-03-22 | From: Sweta Saran SwetaS@microland.com Sent: 22 March 2021 19:14 To: Siddharth Mishra SiddharthM@microland.com RMC Collaboration Team rmccollaborationteam@microland.com Smartcenter Support smartcentersupport2@microland.com Cc: Amardeep Mandrekar AmardeepMaR@microland.com RMC Shift Manager RMCShiftManager@microland.com Ashwin Ananthakrishnan AshwinAK@microland.com Subject: RE: Adding All Menabev CI to SMC Hi Siddharth Our team will do the need full and update the status once done. Thanks Regards Sweta Saran Analyst-Application Support Microland Limited M: 00-1833-257-9404E-mail: SwetaS@microland.com From: Siddharth Mishra [mailto:SiddharthM@microland.com] Sent: Monday March 22 2021 7:01 PM To: RMC Collaboration Team rmccollaborationteam@microland.com Smartcenter Support smartcentersupport2@microland.com Cc: Amardeep Mandrekar AmardeepMaR@microland.com RMC Shift Manager RMCShiftManager@microland.com Ashwin Ananthakrishnan AshwinAK@microland.com Subject: RE: Adding All Menabev CI to SMC Looping SMC Team Regards Siddharth Microland Limited P: 91 9535767583 Weekoff : Friday Saturday From: RMC Collaboration Team rmccollaborationteam@microland.com Sent: Monday March 22 2021 6:59 PM To: Siddharth Mishra SiddharthM@microland.com Cc: Amardeep Mandrekar AmardeepMaR@microland.com RMC Shift Manager RMCShiftManager@microland.com Ashwin Ananthakrishnan AshwinAK@microland.com RMC Collaboration Team rmccollaborationteam@microland.com Subject: RE: Adding All Menabev CI to SMC Hi Siddarth Still we are unable to access SMC portal. Thanks Regards SenthilRMCMicroland Limited Tel: 91 80 61751181Extn: 5181 From: Siddharth Mishra SiddharthM@microland.com Sent: Monday March 22 2021 6:03 PM To: RMC Collaboration Team rmccollaborationteam@microland.com Cc: Amardeep Mandrekar AmardeepMaR@microland.com RMC Shift Manager RMCShiftManager@microland.com Ashwin Ananthakrishnan AshwinAK@microland.com Subject: RE: Adding All Menabev CI to SMC Hi Team Please raise an SR in SMC support portal to add the attached CIs under Menabev customer and map it to RMC Windows workgroup. Regards Siddharth Microland Limited P: 91 9535767583 Weekoff : Friday Saturday From: Amardeep Mandrekar AmardeepMaR@microland.com Sent: Monday March 22 2021 5:57 PM To: Siddharth Mishra SiddharthM@microland.com Subject: Fw: Adding All Menabev CI to SMC Hi Please do the needful Regards Amardeep Mandrekar SME - Wintel Microland Limited 91 7020474707 Shift Timing: 12 - 9 PM Weekly off : Friday Saturday 91 ________________________________________ From: Amardeep Mandrekar Sent: Thursday March 4 2021 3:03 PM To: Ashwin Ananthakrishnan AshwinAK@microland.com Cc: Tushar Bose TusharBK@microland.com Subject: Adding All Menabev CI to SMC HI Ashwin Please help to add all the Menabev CI into SMC as per attached List. currently many are missing in SMC and at time we receive Tickets with Generic CI's Regards Amardeep Mandrekar SME - Wintel Microland Limited 91 7020474707 Shift Timing: 12 - 9 PM Weekly off : Friday Saturday 91 | Sweta Saran | Resolved
2021-03-23 | SR2914879 | SMC RMC | 2021-03-22 | SLA Notification Matrix to be updated. | Venkataramanaiah Katabathina | Work in Progress |  |  |  |  | 23rd Mar: Venkat to close this today 24th Mar: Venkat to close this today
2021-03-23 | SR2914908 | SMC RMC | 2021-03-22 | Hi Team Can you please add workgroup of customer Enzen SGN to the below users in Smartcenter. User Email : UtkalikaD@microland.com ShreyankaSC@microland.com DUR@microland.com MilindM@microland.com RishabSK@microland.com | Mohammed Inayathulla | Resolved |  |  |  |  | 23rd Mar: Mohammed has informed to use the Admin module, the team to check and get back to us.
2021-03-23 | SR2915215 | SMC RMC | 2021-03-23 | Re: Urgent Smart Center Access Required PFA Created by Subhodeep | Mohammed Inayathulla | Resolved |  |  |  |  | 23rd Mar: User creation is done, awaiting confirmation.
2021-03-23 | SR2915395 | SMC RMC | 2021-03-23 | Hi Team Please help us resolve the problem ticket from your end - PM2897751 as we are unable to resolve it. PFA | Sweta Saran | Resolved
2021-03-23 | IM2915422 | SMC KLI | 2021-03-23 | Hi Team Email to ticket conversion feature is not working for app group. PFA mails sent to this generic email. Requesters name Apurva Raut Request description Email to ticket conversion-App Windows ID Autoticket-Groupinstaclaim Email ID Kli-autoticket-groupinstaclaim@kotak.com Ticket creation default path Application management-Group instaclaim-Request | Aravindsagar Venkatesh | Work In Progress |  |  |  |  | 23rd Mar: Aravind is working on this. Will close it today. 24th Mar: Aravind is working on this, there is autodiscover service issue, to be resolved.
2021-03-23 | SR2915490 | SMC New CIS | 2021-03-23 | Hi Team Please make the Employee id and department field mandatory. Ticket cannot be raised with these fields being blank. | Venkataramanaiah Katabathina | On Hold (Customer) |  |  |  |  | 23rd Mar: Venkat to cross check if the engineer is adding a new requestor, or facing blank department and employeeid for existing requestors. We have AD Sync enabled for CIS, so all the details must be filled automatically. 24th Mar: Customer on leave, once the customer is back we can connect.
2021-03-23 | SR2915494 | SMC New CIS | 2021-03-23 | Hi Team Please add employee id column to Reports RP000024 RP000149RP000160 | Mohammed Inayathulla | Resolved |  |  |  |  | 23rd Mar: Mohammed to add the Employeed ID column into the three reports and confirm.
2021-03-23 | SR2915579 | SMC CIS | 2021-03-23 | Hi Team While user selects Dis-satisfied or highly dis-satisfied a comment section link will be displayed where user needs to fill his comments along with it user will select the reason for his ratings from the drop down. In the drop down section Asset quality related issues field to be added for reference added the screenshot in attachment. Please connect with Suvarna K for the queries or additional inputs required. Customer : Ask icroland Service line : CIS Type of ticket : IM SR | Venkataramanaiah Katabathina | Resolved |  |  |  |  | 23rd Mar: Venkat to do the configuration and close the ticket today.
2021-03-23 | IM2915592 | SMC New EFL | 2021-03-23 | Please share current SMC tool “Incident” and “Service Request” approval detail. This information is required for audit FYI attached herewith last year file service request file. | Venkataramanaiah Katabathina | Work In Progress |  |  |  |  | 23rd Mar: Venkat to take the required query from Vignesh, and share the details today. 24th Mar: Vignesh has shared the details. EFL Onsite team to check with Pushpasheel and get back, hence it is on hold.
2021-03-23 | SR2915643 | SMC HMCL | 2021-03-23 | Hi Team Please remove the email ID from the notification. Email ID : anupam.mittal@heromotocorp.com | Sweta Saran | Resolved |  |  |  |  | 23rd Mar: Sweta to do the configuration and close the ticket today.
2021-03-23 | SR2915693 | SMC Automation | 2021-03-23 | From: Raghavendra Seshu Murthy Y Sent: 23 March 2021 12:06 To: Mohammed K MohammedKI@microland.com Venkataramanaiah Katabathina VenkataramanaiahK@microland.com Sweta Saran SwetaS@microland.com Cc: Neetu D NeetuD@microland.com Nandam Kumar NandamKP@microland.com #ML-MACS-CloudInfraSupport MACS-CloudInfraSupport@microland.com Subject: SMC permissions Importance: High Hi Team Please provide permissions to Neetu and Pavan for Cloudappsupport workgroup. Clone ID same as Siva or Lava. Regards Raghavendra Manager-Technology Microland Limited P: 91 80 6175 1000 E: 5555 M: 91 98458 02352 | Mohammed Inayathulla | Resolved |  |  |  |  | 23rd Mar: Mohammed to provide access and close the ticket.
2021-03-23 | SR2915714 | SMC Automation | 2021-03-23 | upload the data from Device to Assets - Enabled Asset Management Feature for All HDU CMDB Enabled customers | Vignesh Annadurai | Work in Progress |  |  |  |  | 23rd Mar: Vignesh to close by or before 25th Mar 24th Mar: Vignesh to close by or before 25th Mar
2021-03-23 | SR2915964 | SMC Automation | 2021-03-23 | Bot End User Portal Form Creation Configuration | Aravindsagar Venkatesh | Resolved |  |  |  |  | 23rd Mar: Aravind to close this by tomorrow 1st half.
2021-03-24 | SR2916216 | SMC New CIS | 2021-03-23 | Hi Team SR2916200 leave reversal ticket has not gone for approval. Please check | Mohammed Inayathulla | On Hold (Customer) |  |  |  |  | 24th Mar: Mohammed to check with Mahesh, Department cannot be blank, after updating the Department name from backend it is working.
2021-03-24 | IM2916248 | SMC KLI | 2021-03-23 | Kindly check as we are not able to assign below assets on user name - Palash Deka KA KLI Employee ID: OM108626 in SMC CPU KLI23392 UXVJSSII64F2540786 KLI - Tezpur TFT Monitor KLI23936 MMT3CSS001527048FE4200 KLI – Tezpur | Venkataramanaiah Katabathina | On Hold (Customer) |  |  |  |  | 24th Mar: AD Sync for KLI is not updated the details on time, Mahesh to check and help on this.
2021-03-24 | SR2916257 | SMC Automation | 2021-03-23 | Test ticket by SmartCenter support team. | smcadmin1 | Resolved
2021-03-24 | SR2916430 | SMC HMCL | 2021-03-23 | User detail not matching in Smartcenter as per the Google contacts. Snap enclosed please refer the snap of Google contacts and update the detail in smartcenter. | Venkataramanaiah Katabathina | Resolved
2021-03-24 | SR2916490 | SMC Automation | 2021-03-23 | Please check today's automated report | Mohammed Inayathulla | Resolved
2021-03-24 | SR2916495 | SMC CIS | 2021-03-23 | Hi Mohammed Please add 'Disconnected' option in status dropdown | Mohammed Inayathulla | Resolved
2021-03-24 | SR2916535 | SMC RMC | 2021-03-23 | RE: Category Catalogue required | Sweta Saran | Resolved
2021-03-24 | SR2916686 | SMC KLI | 2021-03-23 | For some category the Classification field automatically taking as ‘Others-Undefined’. If you check we have not provided ‘Others-Undefined’ for all categorysubcategory but still its taking automatically. Few eg. With ticket no. given below please check urgently. Eg. Service Request- Desktop Common Drive Access LAN User VPN User VDI User Outlook Email Ms-Outlook - Configuration LAN User VPN User VDI User Laptop Laptop - Temporary Allocation LAN User VPN User VDI User Incident – Outlook Email MSOutlook Not able to sendreceive mails LAN User VPN User VDI User Outlook Email MSOutlook Not able to open attachment LAN User VPN User VDI User SR1546336 SR1542582 SR1543050 IM1536709 IM1543546 IM1544864 IM1544358 IM1545695 IM1540872 | Sweta Saran | Work in Progress |  |  |  |  | 24th Mar: Sweta to check and get on to screensharing session with KLI Team for further understanding and troubleshooting.
2021-03-24 | IM2916769 | SMC RMC | 2021-03-23 | Hi Team The Dashboards don't show any options like Weekly Monthly for My SMC logon: JithuJR@microland.com It only gives me an option My Worklist clicking on which I don't see any options to navigate to different views. Requesting to look into the issue at the earliest possible. Warm regards Jithu J | Venkataramanaiah Katabathina | Work In Progress |  |  |  |  | 24th Mar: We need to ask the user to connect with the Ops Excellence team for all Dashboarding relating understandings. If the are any clarifications or changes required they will be able to help, and they are the SPoC for SmartCenter team.
2021-03-24 | IM2916866 | SMC RMC | 2021-03-23 | Hi Team The automated dashboards show the Resolution SLA target for Bunge as 95 which is incorrect. The Resolution SLA target for Incident P3 is 97 for Bunge. Requesting to make the necessary changes. Warm regards Harry | Sweta Saran | Work In Progress |  |  |  |  | 24th Mar: Coordinate and setup a session between Utkal and Harry from Ops Excellence team. Utkal will be able to help in this.
2021-03-24 | SR2917194 | SMC RMC | 2021-03-24 | Hi SMC Team We have sent resolved docket notification through SMC Outage Module for the subjected ticket. In Smartcenter we can see the docket but we didn't receive it over mail request you to check from backend and assist to resolve the issue. PFA | Mohammed Inayathulla | Work in Progress |  |  |  |  | 24th Mar: Ask for which customer it is, take the email id from NotificationServiceEmail Config table, login to this mailbox, and check in the sent items, if that docket email was sent. If it is sent you can provide a screenshot as evidence.
2021-03-24 | SR2917460 | SMC RMC | 2021-03-24 | Our Engineers are unable to place the ticket on Hold in SMC as the option keeps on loading and does not allow us to proceed with placing the ticket on hold. PFA | Venkataramanaiah Katabathina | On Hold (Customer) |  |  |  |  | 24th Mar: Reconfirm and close this ticket. The sample ticket is already moved to On Hold (Customer).
2021-03-24 | SR2917516 | SMC Automation | 2021-03-24 | Hello AnandNatarajan Could you please help removing the notifications below 75 to my ID? Regards Jithu | Mohammed Inayathulla | Resolved
2021-03-24 | IM2917620 | SMC New EFL | 2021-03-24 | Hi Team Please change email ID below. User ID: Pratikshass OLD ID: Pratikshass@microland.com New ID:Pratikshasas@microland.com User ID: ShubhamD old id: Shubhamd@microland.com New ID: I_ShubhamD@microland.com | Sweta Saran | Work in Progress |  |  |  |  | 24th Mar: Sweta to do the change and close it today.
2021-03-24 | IM2917646 | SMC KLI | 2021-03-24 | Unable to remove user name - Mahesh Junagade Tied KLI Employee ID: OM35282 from SMC asset tag No. KLI26589 Please resolve the issue. | Sweta Saran | Work In Progress |  |  |  |  | 24th Mar: Asset Detagging, while assigning the asset the relationship is inserted as null, which is the cause of this issue. for this ticket we can update the field and allow the detagging to be done. But talk to Parameswar and get the troubleshooting done for the actual cause above.
2021-03-24 | SR2917744 | SMC Automation | 2021-03-24 | Sonic wall CMDB data upload | Aravindsagar Venkatesh | Work in Progress

## Sheet2
ticketNo | statusName
IM2750933 | Work in Progress
IM2806674 | On Hold (Customer)
IM2807685 | On Hold (Customer)
SR2835148 | Work in Progress
IM2835284 | On Hold (Customer)
SR2844980 | On Hold (Customer)
SR2851582 | On Hold (3rd Party)
SR2857896 | On Hold (3rd Party)
SR2867998 | On Hold (Customer)
IM2875114 | On Hold (3rd Party)
SR2900432 | On Hold (Customer)
IM2900504 | On Hold (Customer)
IM2900564 | On Hold (3rd Party)
SR2905188 | On Hold (Customer)
IM2906237 | Work In Progress
IM2908573 | Resolved
SR2908977 | Resolved
SR2909621 | On Hold (Customer)
SR2909630 | Resolved
IM2910128 | Work in Progress
SR2910355 | Work in Progress
SR2910360 | Work in Progress
SR2910371 | Work in Progress
IM2910469 | Work in Progress
IM2910605 | Work In Progress
SR2910790 | Work in Progress
IM2911199 | On Hold (Customer)
SR2913186 | Resolved
SR2913513 | Resolved
IM2913987 | Work In Progress
SR2914879 | Work in Progress
SR2914908 | Resolved
SR2915215 | Resolved
IM2915422 | Work In Progress
SR2915490 | On Hold (Customer)
SR2915494 | Resolved
SR2915579 | Resolved
IM2915592 | Work In Progress
SR2915643 | Resolved
SR2915693 | Resolved
SR2915714 | Work in Progress
SR2915964 | Resolved

## Resolution 12th Mar
ticketNo | description | assignedToName | Resolved By | Resolved Time | Work Done By
2847548 | Hi Team Need to add User KM articles on EUP portal . User has to refer the KM article as L1 troubleshooting if issue is not resolved then user must be able to raise ticket get assistance from CIS team. Please check the feasibility on this requirement action accordingly to have KM articles in EUP portal. For clarifications please connect Suvarna K and Muniraja K | Vignesh Annadurai | Vignesh Annadurai | 44267.6518
2877571 | Hi Team Please deactivatedisable below workgroups from SMC dashboard for the customer Jubilant Pharma. DCTeamMontreal DCTeamOrlando DCTeamSpokane DCTeamYardley RMC Managers RMC SOC SecurityTeamOrlando Regards Likhithosh K S | Sweta Saran | Sweta Saran | 44267.5107
2882771 | Dear Team We are not getting On call Hardware and on call software ticket CSAT Score in Weekly and Monthly basis report. For more details please contact Mrs. Archita 7319482285. Regard's Roojvelt | Venkataramanaiah Katabathina | Venkataramanaiah Katabathina | 44267.7829 | Mahesh
2891345 | user location is showing as default | mohammed inayathulla | mohammed inayathulla | 44267.635
2896121 | Hi SMC Team Please help in sharing the data mentioned in Email trail as we are facing issue while raising a ticket. Thanks Regards | mohammed inayathulla | mohammed inayathulla | 44267.4732
2897881 | Please refer attached some additional keywords for Service Request kindly add into the configuration. | Venkataramanaiah Katabathina | Venkataramanaiah Katabathina | 44267.7628 | Venkat
2899550 | Dear SMC Team Request you to please provide access to my ID as it was working earlier. ID : kajoshi2 Mo Number: 8879486961 | mohammed inayathulla | mohammed inayathulla | 44267.4843
2899770 | we are not able to assign user name - Singh Yogita FMG KLI Employee ID: OM107827 in below asset tag CPU KLI30490 UXB1JSIZ08I2625480 KLI - Hissar 3 TFT Monitor KLI27161 MMT6MSS00162900DF73E00 KLI - Hissar 3 | Venkataramanaiah Katabathina | Venkataramanaiah Katabathina | 44267.6198 | Venkat
2899804 | Hi Muhammed As discussed request you to please assist Sagar for Smartcenter login. He can reach him on 916372376494 and email id SagarMi@microland.com Regards Suhas From: Mohammed K Sent: 10 March 2021 11:03 To: Suhas Panchal Aravindsagar Venkatesh Smartcenter Support Cc: Vignesh Annadurai Anand Kannan Tobias Wilson Naresh Kumar Suraj Sutar Subject: RE: Login id creation for Sagar Mishra Hi Suhas The URL is not correct which you are trying to access to create ticket from khaitan account. Anyhow the account for Sagar has been created please check. | Venkataramanaiah Katabathina | Venkataramanaiah Katabathina | 44267.6446 | Venkat
2900346 | Unable to remove user name - Apurba Bhagawati Tied KLI Employee ID: OM21401 from SMC asset tag No. KLI25134 Please resolve the issue. | Venkataramanaiah Katabathina | Venkataramanaiah Katabathina | 44267.4416 | Venkat
2900347 | Unable to remove user name - Arindom Dey KA KLI Employee ID: OM36873 from SMC asset tag No. KLI05415 Please resolve the issue. | Venkataramanaiah Katabathina | Venkataramanaiah Katabathina | 44267.4412 | Venkat
2900512 | Hi Team Requesting to provide access to the Customer Bunge on SMC Username: BhavanaSK@microland.com Warm regards Bhavana | Sweta Saran | Sweta Saran | 44267.5093
2901279 | Need to disable the duplicates rules. | Venkataramanaiah Katabathina | Venkataramanaiah Katabathina | 44267.7678 | Venkat
2901347 | Adding Subcategory and classification details requested by Nupur | Venkataramanaiah Katabathina | Venkataramanaiah Katabathina | 44267.8171 | Vankat